## Slide 1
FUTUREREADY NYC · NYCPS OFFICE OF STUDENT PATHWAYS
RECRUITMENT
& RETENTION
PLAYBOOK
A school-year action guide for FRNYC teams Grade by grade · Month by month · Aligned to KIMs
2026 · FUTUREREADY NYC · VERSION 4

## Slide 2
RECRUITMENT & RETENTION PLAYBOOK
WHAT THIS PLAYBOOK IS FOR
This playbook guides FRNYC school teams through what to do — grade by grade, month by month — to build a full, equitable cohort and retain students through credential completion. Each activity is linked to its relevant KIM checkpoint so teams can see how their work connects to accountability. FRNYC places students in career pathways combining Work-Based Learning (WBL), college-credit coursework (ECC), and industry credentials. Enrollment officially begins in 10th grade; 8th–9th grade is for awareness and interest alignment.
WHO THIS IS FOR
FRNYC Coordinators
manage the full cycle from awareness to completion
School Counselors
lead 1:1 advising, planning, and early intervention
APs of Instruction
schedule ECC supports; lead end-of-year debrief
Pathway Teachers
deliver career exploration and CCI; connect to WBL
KIM CHECKPOINTS — SCHOOL YEAR OVERVIEW
CHECKPOINT A
Oct 5, 2025
Cohort in STARS · Fall CCI enrolled Equity & support plans · WBL intermediary confirmed
CHECKPOINT B
Jan 5, 2026
First 1:1 advising complete First unpaid WBL captured · Spring ECC planning confirmations
CHECKPOINT C
Apr 5, 2026
11th–12th ECC enrolled · 9th career exploration enrolled Seniors: paid WBL accepted/confirmed
CHECKPOINT D
Jul 5, 2026
All completions locked · 2nd 1:1 done Career plans filed · Year-end reflection & next-SY planning
WHAT SUCCESS LOOKS LIKE IN SCHOOLS — 5 CORE PRINCIPLES OF RECRUITMENT
1. TIMING
Recruitment is year-round, starting before students enter high school. Programs that delay until 10th grade struggle. Strong programs begin in 8th grade.
2. INTEGRATION
Programs embedded in advisory, courses, and school culture see stronger enrollment and persistence than those that operate as separate add-ons.
3. SOCIAL PROOF
Students are most influenced by other students. Peer-to-peer communication builds trust, makes pathways feel real, and increases enrollment.
4. RELEVANCE
Students enroll and stay when they understand what they'll do and gain. Lead with concrete outcomes — not abstract language like 'career readiness.'
5. EQUITY
Students with disabilities and multilingual learners are often underrepresented due to structural barriers — not lack of interest. Strong programs track representation, identify barriers, and address them before they become attrition. See the Equity Checklist on the final page. Linked to KIMs A6 and D31.
2
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 3
8TH GRADE — AWARENESS & OUTREACH
PRE-KIM AWARENESS & OUTREACH
8TH GRADE
Goal: 8th graders and families know your school is a FRNYC school and are interested enough to choose it.
8
WHEN
ACTIVITY
PURPOSE & SUCCESS
AUDIENCE
POINT PERSON
CATEGORY
KIM
Sept–Oct
Promote FRNYC on all school materials
Add FRNYC branding to website, flyers, social posts. Lead with outcomes: ECC credits, WBL, credentials. Success: Visitors know you're a FRNYC school before they arrive.
Prospective families
FRNYC Coordinator
Recruitment
No direct KIM Supports A6
Oct–Feb
Ambassador-led open house
Brief 2–3 FRNYC students; assign to small groups. Each shares one concrete outcome they earned. Success: 8th graders hear a real outcome from a current student.
Prospective students (8th)
FRNYC Coordinator
Recruitment
No direct KIM Pipeline to A3
Oct–Feb
Feeder school outreach + invite to FRNYC event
Contact 3–5 feeder school counselors; offer tour or ambassador visit. Invite 8th graders to showcase — no application required. Success: 2+ feeder visits done; students see FRNYC in action.
Prospective students & families
FRNYC Coordinator
Recruitment
No direct KIM Supports A6
Year 0 tip: Start with your own students first. Identify 2–3 excited 10th or 11th graders and prepare them as ambassadors before any external outreach. Each one shares: one outcome earned, one thing learned, and why they chose this pathway.
KIM REFERENCE
A6
Plan to equitably recruit & support underserved groups — nearest KIM anchor for 8th-grade outreach
A3
10th–12th graders in STARS — downstream outcome these activities build toward
3
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 4
9TH GRADE — EXPLORATION & COHORT CONVERSION
EXPLORATION & INTEREST ALIGNMENT → COHORT CONVERSION
9TH GRADE
Goal: Every 9th grader explores career options and can say whether FRNYC fits. Cohort confirmed before year-end. KIM chain: C20 → D32 → D34 → D30.
9
WHEN
ACTIVITY
PURPOSE & SUCCESS
AUDIENCE
POINT PERSON
CATEGORY
KIM
Sept–June
Career Explorations — all 9th graders
Cover multiple career areas. Each student names one career area + one reason why. Success: Every 9th grader can say whether FRNYC fits.
Enrolled 9th graders
Pathway Teacher
Recruitment
C20 · D37
Oct & Mar
Ambassador visits to 9th grade advisories
Two visits per year using Advisory Slide Deck. Ambassadors share one thing they've done and earned. Success: Every 9th grader has 2+ FRNYC exposures before the survey.
Enrolled 9th graders
FRNYC Coordinator
Recruitment
No direct KIM Builds to D30
Nov or Feb
Parent-student panel
3–4 FRNYC students share what they've done; parents ask questions. Success: Parents can describe one concrete outcome students earn.
9th grade families
FRNYC Coordinator
Recruitment
No direct KIM Supports A6
End of March
Interest survey — all 9th graders
Google Form — required (Yes / No / Maybe); 1–2 sentence explanation. Follow up non-responders within 5 days. Success: 100% response rate; sorted list by end of March.
Enrolled 9th graders
FRNYC Coordinator
Recruitment
D32
April
1:1 meetings with interested students
Survey response is the agenda. Scheduling conflicts get a conversation, not exclusion. Success: Every interested student has a documented 1:1 by end of April.
Interested 9th graders
School Counselor
Recruitment
D34
By May
Orientation for rising 10th graders + parent session
Rising 10th graders meet teacher and cohort. Parent session covers what students earn + key dates. Success: Rising 10th graders enter September knowing pathway, cohort, and teacher.
Confirmed students & families
FRNYC Coordinator
Recruitment
D30
Timing matters: Deploy the survey by end of March — not May. This gives you April for real 1:1 conversations and time to complete orientation before year-end. 'Maybe' triggers a follow-up, not an exclusion.
4
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 5
10TH GRADE — COHORT LAUNCH & EARLY EXPERIENCE
COHORT LAUNCH & DEEP ENGAGEMENT
10TH GRADE
Goal: Students officially in FRNYC as a cohort. WBL aligned with CCI. Peer community forms. All in STARS and CCI enrolled by Checkpoint A (Oct 5).
10
WHEN
ACTIVITY
PURPOSE & SUCCESS
AUDIENCE
POINT PERSON
CATEGORY
KIM
September
STARS enrollment + cohort launch event
Confirm all 10th graders in STARS. Inaugural event: welcome students by name; older FRNYC students share one thing earned. Success: Every student in STARS; students feel publicly welcomed.
Enrolled 10th graders
FRNYC Coordinator
Retention
A3 · A8
Sept–Oct
Align WBL with CCI via intermediary partner
Share CCI overview with WBL intermediary (assigned by OSP). Confirm 100% have pathway-aligned WBL placement by October. Success: Every student sees connection between coursework and real-world experience.
Enrolled 10th graders
FRNYC Coordinator
Retention
B17 · D43
Monthly
Monthly FRNYC community time
30–60 min during advisory, lunch, or after school. Unite students across CCI sections — cross-section peer network is the primary retention driver. Success: Students attend consistently; peer relationships deepen.
Enrolled 10th graders
FRNYC Coordinator
Retention
Supports B15
Per semester
Family checkpoint events
One event per semester. Answer: What will my student earn? What skills? What real-world experience? What's the post-graduation benefit? Translate into top 3 home languages. Success: Parents can describe what their student is earning.
Families of enrolled students
FRNYC Coordinator
Retention
Supports A6
KIM REFERENCE
A3
Cohort in STARS — Oct 5
A8
Fall CCI enrolled — Oct 5
B17
First unpaid WBL captured — Jan 5
D43
Two unpaid WBL completed — Jul 5
5
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 6
11TH GRADE — PERSISTENCE, SUPPORTS & POST-SECONDARY PLANNING
ACADEMIC SUPPORTS, ADVISING & ECC PERSISTENCE
11TH GRADE
Goal: ECC supports scheduled into the school day — not optional add-ons. Every student builds a post-secondary plan grounded in their FRNYC experience.
11
WHEN
ACTIVITY
PURPOSE & SUCCESS
AUDIENCE
POINT PERSON
CATEGORY
KIM
Sept–Oct
ECC eligibility audit + support planning
Identify who needs support (placement scores, GPA, prerequisites). AP schedules tutoring or Regents prep inside the school day. Coordinate deadlines with ECC partner. Success: Every student has a clear ECC path; support plan in place by Oct 5.
Enrolled 11th graders
AP of Instruction
Retention
A7 · C24
January
First structured 1:1 advising + early intervention
1:1 connecting CCI/WBL work to post-graduation goals. Warning: 3+ missed sessions, declining grades, or disinterest → 1:1 within 1 week; document discussion and commitments. Success: All students have had first advising 1:1 by January 5.
Enrolled 11th graders
School Counselor
Retention
B15
Feb–May
Group sessions + ongoing early intervention
2+ structured group sessions connecting CCI and WBL to post-graduation goals. Track attendance; flag anyone missing 2+. No student exits without a documented conversation. Success: All at-risk students have documented intervention notes.
Enrolled 11th graders
FRNYC Coordinator
Retention
A7 · D40
Before June
Second 1:1 + post-secondary plan documented
Ask: 'Based on your FRNYC work, what do you want after graduation?' Document: WBL experiences, ECC completed, intended next step. Use Post-Secondary Planning Template from OSP. Success: Every student has a documented post-secondary intention before year-end.
Enrolled 11th graders
School Counselor
Retention
D33 · D36
KIM REFERENCE
A7
Academic supports plan — Oct 5
B15
First 1:1 complete — Jan 5
C24
ECC enrollment confirmed — Apr 5
D33
Second 1:1 complete — Jul 5
D36
Written career planning reflection — Jul 5
D40
ECC completion — Jul 5
D44
Paid WBL completion benchmark — Jul 5
6
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 7
12TH GRADE — COMPLETION, CYCLE RENEWAL & EQUITY
COMPLETION & AMBASSADOR PIPELINE
12TH GRADE
Goal: Every enrolled student earns their credential before graduation. At-risk students identified in September. Completers become next year's ambassadors.
12
WHEN
ACTIVITY
PURPOSE & SUCCESS
AUDIENCE
POINT PERSON
CATEGORY
KIM
September
KIM review — on-track vs. needs-support list
Pull each student's ECC record. On-track vs. needs-support. By Oct 1: every at-risk student has a written completion plan — Coordinator tracks, Principal accountable. Success: Every student's ECC status known by October 1.
Enrolled 12th graders
FRNYC Coordinator
Retention
A7 · Protects D40
Ongoing
ECC partner coordination
Name a direct contact at ECC partner; know all enrollment, withdrawal, and grade reporting deadlines. When a student is at risk, contact the ECC liaison directly — before mid-semester, when options narrow. Success: No credit lost due to a missed administrative deadline.
School / ECC partner
FRNYC Coordinator
Retention
B16 · D41 · D42
Jan–Apr
Completion push + ambassador recruitment
January: verify ECC progress; weekly check-ins for anyone behind — name exactly what to complete and by when. Recruit 3–5 completing seniors as ambassadors — ask directly; role: open house, advisory visits, share experience. Success: 90%+ earn credential before graduation; 3+ ambassadors confirmed.
Enrolled 12th graders
FRNYC Coordinator
Both
C25 · D40 · D46
Before June 30
End-of-year debrief
Coordinator + AP + Counselor: review % who completed, where drop-offs occurred, 3 specific changes for next cycle. File debrief before June 30 — findings shape next fall. Success: Written debrief on file; 3 changes identified for next year.
School staff
FRNYC Coordinator
Both
D29 · D31
KIM REFERENCE
A7
At-risk support plans — Oct 5
B16
Spring ECC planning confirmations — Jan 5
C25
Seniors: paid WBL accepted — Apr 5
D40
ECC completion — Jul 5
D46
Seniors: paid WBL completed — Jul 5
D29
Next-SY implementation plan — Jul 5
D31
Equity reflection complete — Jul 5
7
FutureReady NYC · NYCPS Office of Student Pathways

## Slide 8
EQUITY CHECKLIST & KIM CROSSWALK
EQUITY CHECKLIST — SWD & MLL ACCESS (REVIEW AT ENROLLMENT AND MID-YEAR)
BARRIER TO WATCH FOR
WHAT TO DO
IEP mandated services or pull-out schedules create conflicts that block SWD students from the cohort — often without anyone flagging it
Cross-reference the Yes/Maybe survey list with the master schedule before the cohort is finalized. Students blocked get a 1:1 — explore period swaps, modified pull-outs, or an alternate CCI section. Flag to AP before cohort finalized.
Open house materials, interest survey, and pathway descriptions are English-only
Translate all core materials into the top 3 home languages. Request support from ENL or your network office. Recruit bilingual student ambassadors.
ECC partner prerequisites may screen out SWD and MLL students who qualify via different pathways
Audit prerequisite lists annually. Identify confirmed partner requirements vs. internal assumptions that can be challenged. Escalate structural barriers to your AP and OSP.
SWD / MLL enrollment in FRNYC is significantly below their share of the school population
Set an explicit equity target before each cycle. Actively recruit early. Escalate significant gaps to school leadership and OSP before October 1.
KIM CROSSWALK — ALL GRADES AT A GLANCE
KIM
DESCRIPTION
DUE
GRADE
PLAYBOOK ACTIVITY
A3
All FRNYC 10th–12th graders in STARS
Oct 5
10th
STARS enrollment + cohort launch
A6
Plan to equitably recruit underserved students
Oct 5
All
Outreach, open house, feeder schools, equity targets
A7
Plan for academic supports & remediation
Oct 5
11–12th
ECC audit (11th) · KIM review (12th)
A8
All FRNYC students enrolled in Fall CCI
Oct 5
10th
STARS enrollment + cohort launch
B15
First 1:1 advising complete
Jan 5
11th
First structured 1:1 advising
B17
First unpaid WBL captured in STARS
Jan 5
10th
WBL alignment with intermediary
C20
9th graders enrolled in career exploration course
Apr 5
9th
Career Explorations
C24
11th–12th enrolled in pathway-aligned ECC
Apr 5
11th
ECC eligibility audit + supports
C25
Seniors: pathway-aligned paid WBL accepted/confirmed
Apr 5
12th
Completion push (Jan–Apr)
D30
Rising 10th graders identified in STARS
Jul 5
9th
Orientation for rising 10th graders
D32
9th graders completed career interest survey
Jul 5
9th
Interest survey (March)
D34
9th graders completed 1:1 with advisor
Jul 5
9th
1:1 meetings with interested students (April)
D36
All FRNYC students: written career planning reflection
Jul 5
11th
Second 1:1 + post-secondary plan
D40
All FRNYC 11th–12th: completed ECC
Jul 5
11–12th
ECC supports + completion push
D43
All 10th graders: two unpaid WBL activities completed
Jul 5
10th
WBL alignment with intermediary
D31
Equity reflection complete
Jul 5
All
End-of-year debrief
D29
Next-SY budget & implementation plan approved
Jul 5
12th
End-of-year debrief
8
FutureReady NYC · NYCPS Office of Student Pathways