## Slide 1
FUTUREREADY NYC · NYCPS OFFICE OF STUDENT PATHWAYS
RECRUITMENT & RETENTION PLAYBOOK
A school-year action guide for FRNYC teams. Grade by grade. Month by month. Aligned to KIMs.
2026 · FUTUREREADY NYC

## Slide 2
Recruitment & Retention Playbook
WHAT THIS PLAYBOOK IS FOR
This playbook guides FRNYC school teams through what to do — grade by grade, month by month — to build a full, equitable cohort and retain students through credential completion. Each activity is linked to its relevant KIM checkpoint. FRNYC places students in career pathways combining Work-Based Learning (WBL), college-credit coursework (ECC), and industry credentials. Enrollment officially begins in 10th grade; 8th–9th grade is for awareness and interest alignment.
WHO THIS IS FOR
• FRNYC Coordinators — manage the full cycle from awareness to completion
• School Counselors — lead 1:1 advising, post-secondary planning, early support
• APs of Instruction — schedule ECC supports; lead end-of-year debrief
• Pathway Teachers — deliver CCI coursework; connect students to WBL
KIM CHECKPOINTS — SCHOOL YEAR OVERVIEW
CHECKPOINT A
Oct 5, 2025
• All 10th–12th graders identified in STARS [A3] • All students enrolled in Fall CCI [A8] • Equity recruitment and support plan submitted [A6] • Academic support plan in place for students who need it [A7] • WBL intermediary partner confirmed for 10th grade
CHECKPOINT B
Jan 5, 2026
• All 11th graders: first 1:1 with college & career advisor complete [B15] • Spring ECC planning confirmations completed [B16] • All 10th graders: first unpaid WBL activity captured in STARS [B17]
CHECKPOINT C
Apr 5, 2026
• All 9th graders enrolled in career exploration course [C20] • All 11th–12th graders enrolled in pathway-aligned ECC [C24] • All 12th graders: paid WBL opportunity accepted and confirmed [C25]
CHECKPOINT D
Jul 5, 2026
• Next school year implementation plan approved [D29] • All rising 10th graders identified in STARS [D30] • Annual equity reflection complete [D31] • 9th grade: interest survey, 1:1 advising & exploration complete [D32, D34, D37] • ECC completions locked; WBL activities documented [D40, D43, D46]
5 CORE PRINCIPLES OF RECRUITMENT & RETENTION
1. TIMING
Recruitment is year-round, starting before students enter high school. Programs that build awareness in 8th grade give students time to explore and arrive in 10th grade ready to engage.
2. INTEGRATION
Programs embedded in advisory, courses, and school culture see stronger enrollment and persistence. When FRNYC is woven into the school day, students experience it as a natural part of their education.
3. SOCIAL PROOF
Students are most influenced by other students. Peer-to-peer communication builds trust, makes pathways feel real, and increases interest and enrollment across all grades.
4. RELEVANCE
Students enroll and stay when they understand what they will do, what they will gain, and how it connects to their future. Lead with concrete outcomes — not abstract language like 'career readiness.'
5. EQUITY
Students with disabilities and multilingual learners are often underrepresented due to structural barriers — not lack of interest. Strong programs track representation, identify barriers, and address them proactively. Linked to KIMs A6 and D31.
KEY TERMS USED IN THIS GUIDE
FRNYC
FutureReady New York City — the program this guide supports
KIM
Key Indicator Measure — accountability checkpoint system
WBL
Work-Based Learning — internships, job shadows, workplace simulations
ECC
Employer-Connected Credentials — college-credit coursework aligned to credentials
CCI
College and Career Institute — the FRNYC instructional course framework
STARS
NYC's student data system — all cohort and activity data must be entered here
SWD
Students with Disabilities
MLL
Multilingual Learners
OSP
Office of Student Pathways (NYCPS) — the office that oversees FRNYC
Intermediary
Third-party org assigned by OSP that arranges all WBL placements
"Lead with what students get — a real-world WBL experience (internship, job shadow, or workplace simulation), college credit, or an industry-recognized credential before graduation — not with what FRNYC is or does."
FRNYC Recruitment & Retention Playbook · FutureReady NYC / NYCPS Office of Student Pathways
2

## Slide 3
GRADES 8–9 — AWARENESS, EXPLORATION & COHORT CONVERSION
PRE-KIM AWARENESS & OUTREACH
8TH GRADE
Goal: 8th graders and their families know your school is a FRNYC school and are interested enough to choose it. KIM measurement begins in 10th grade, so this groundwork is strategically essential.
8
When | Activity | Purpose & Success | Audience | Point Person | Cat. | KIM
Sept–Oct | Promote FRNYC on all school materials | □ Add 'Future Ready NYC' and FRNYC logos to website, flyers, and social posts □ Lead with outcomes students earn: ECC credits, WBL experience, industry credentials Success: Visitors know you're a FRNYC school before they arrive at open house. | Prospective families | FRNYC Coordinator | Recruitment | Supports A6 equitable recruitment plan
Oct–Feb | Ambassador-led open house | □ Brief 2–3 current FRNYC students using the Ambassador Script; assign to small groups □ Each ambassador shares one concrete outcome they earned Success: 8th graders hear a real outcome from a current student. | Prospective students | FRNYC Coordinator | Recruitment | Builds pipeline to A3 cohort identification
Oct–Feb | Feeder school outreach + invite to FRNYC event | □ Contact 3–5 feeder school counselors; offer a campus tour or ambassador visit □ Invite prospective 8th graders to a student showcase or career fair — no application required Success: 2+ feeder visits done; prospective students see FRNYC in action. | Prospective students & families | FRNYC Coordinator | Recruitment | Supports A6 equitable pipeline
EXPLORATION & INTEREST ALIGNMENT → COHORT CONVERSION
9TH GRADE
Goal: Every 9th grader explores career options and can say whether FRNYC fits. Cohort confirmed and orientation done before end of year. KIM chain: C20 → D32 → D34 → D30.
9
When | Activity | Purpose & Success | Audience | Point Person | Cat. | KIM
Sept–June | Career Explorations — all 9th graders | □ Cover multiple career areas; ask 'Which connects to something you care about?' □ By end of unit, each student names one career area that interests them Success: Every 9th grader can say whether FRNYC fits. | Enrolled 9th graders | Pathway Teacher | Recruitment | C20 9th enrolled in exploration D37 9th completed exploration
Oct & Mar | Ambassador visits to 9th grade advisories | □ Two visits per year (fall and spring) using the Advisory Slide Deck □ Ambassadors share one thing they've done and one thing they've earned Success: Every 9th grader has 2+ direct FRNYC exposures before the survey. | Enrolled 9th graders | FRNYC Coordinator | Recruitment | Builds pipeline to D30 rising 10th in STARS
Nov or Feb | Parent-student panel | □ 3–4 current FRNYC students share outcomes; parents hear directly and ask questions □ Format: 30–45 minutes, Q&A included Success: Parents can describe one concrete outcome students earn in FRNYC. | 9th grade families | FRNYC Coordinator | Recruitment | Supports A6 equity & family access
End of March | Interest survey — all 9th graders | □ Google Form to every 9th grader — required (Yes / No / Maybe) □ Coordinator follows up with non-responders within 5 days; sort responses by end of March Success: 100% response rate; sorted list by end of March. | Enrolled 9th graders | FRNYC Coordinator | Recruitment | D32 9th graders completed career interest survey
April | 1:1 meetings with interested students | □ 1:1 with each interested student; survey response is the agenda □ Cross-reference with master schedule — conflicts get a conversation, not an exclusion Success: Every interested student has had a documented 1:1 by end of April. | Interested 9th graders | School Counselor | Recruitment | D34 9th graders completed 1:1 with advisor
By May | Orientation for rising 10th graders + parent session | □ Rising 10th graders meet their pathway teacher and cohort □ Same-day parent session covers what students will earn and key dates for the year ahead Success: Rising 10th graders enter September knowing their pathway, cohort, and teacher. | Confirmed students & families | FRNYC Coordinator | Recruitment | D30 Rising 10th graders identified in STARS
FRNYC Recruitment & Retention Playbook · FutureReady NYC / NYCPS Office of Student Pathways
3

## Slide 4
GRADES 10–11 — COHORT LAUNCH, DEEP ENGAGEMENT & ECC PERSISTENCE
COHORT LAUNCH & DEEP ENGAGEMENT
10TH GRADE
Goal: Students are officially in FRNYC as a cohort. WBL aligns with CCI coursework. Peer community and identity form. All students in STARS and enrolled in Fall CCI by Checkpoint A (Oct 5).
10
When | Activity | Purpose & Success | Audience | Point Person | Cat. | KIM
September | STARS enrollment + cohort launch event | □ Confirm all FRNYC 10th graders identified in STARS □ Hold an inaugural event — welcome students by name; invite older FRNYC students to share something they've earned Success: Every student in STARS; students feel publicly welcomed into FRNYC. | Enrolled 10th graders | FRNYC Coordinator | Retention | A3 Cohort in STARS A8 Fall CCI enrolled
Sept–Oct | Align WBL with CCI via intermediary partner | □ Share CCI course overview with the WBL intermediary partner — they arrange all placements □ Confirm 100% of students have a pathway-aligned WBL placement by October Success: Every student sees the connection between coursework and real-world experience. | Enrolled 10th graders | FRNYC Coordinator | Retention | B17 First unpaid WBL captured D43 Two unpaid WBL completed
Monthly | Monthly FRNYC community time | □ 30–60 min monthly session (advisory, lunch, or afterschool) using the Cohort Meeting Guide □ If students span multiple CCI sections, use this time to unite them — cross-section peer network is the primary retention driver Success: Students attend consistently; peer relationships deepen across sections. | Enrolled 10th graders | FRNYC Coordinator | Retention | Retention — peer community and cohort identity
Per semester | Family checkpoint events | □ One event per semester — showcase, career panel, or Career Discovery Week; translate all materials into top 3 home languages □ Answer: What will my student earn? What skills? What real-world experience? Success: Parents can describe what their student is earning in the program. | Families of enrolled students | FRNYC Coordinator | Retention | Supports A6 equity & family engagement
ACADEMIC SUPPORTS, ADVISING & ECC PERSISTENCE
11TH GRADE
Goal: Academic supports for ECC eligibility are scheduled into the school day — not optional add-ons. Every student builds a post-secondary plan grounded in their FRNYC experience.
11
When | Activity | Purpose & Success | Audience | Point Person | Cat. | KIM
Sept–Oct | ECC eligibility audit + support planning | □ Identify who needs support to meet ECC eligibility (placement scores, GPA, or prerequisites) □ AP of Instruction schedules tutoring or Regents prep inside the school day Success: Every student has a clear ECC path; support plan in place by Oct 5. | Enrolled 11th graders | AP of Instruction | Retention | A7 Academic supports plan C24 ECC enrolled Fall/Spring
January | First structured 1:1 advising + early support | □ Structured 1:1 with college & career advisor connecting CCI and WBL work to post-graduation goals □ Watch for: 3+ missed sessions, changing interests, or declining grades — check-in within 1 week Success: All students have had first advising 1:1 by January 5. | Enrolled 11th graders | School Counselor | Retention | B15 First 1:1 with college & career advisor
Feb–May | Group sessions + ongoing support | □ 2+ structured group sessions per year connecting CCI and WBL work to post-graduation goals □ Maintain attendance list; follow up with anyone who misses 2+ Success: Attendance tracked; every student who needs support has a documented plan. | Enrolled 11th graders | FRNYC Coordinator | Retention | A7 Supports plan D40 ECC completion
Before June | Second 1:1 + post-secondary plan documented | □ Ask each student: 'Based on your FRNYC work, what do you want after graduation?' □ Document each student's plan: WBL experiences, ECC courses completed, and intended next step Success: Every student has a documented post-secondary intention before school ends. | Enrolled 11th graders | School Counselor | Retention | D33 Second 1:1 complete D36 Written career planning reflection
FRNYC Recruitment & Retention Playbook · FutureReady NYC / NYCPS Office of Student Pathways
4

## Slide 5
12TH GRADE — COMPLETION & AMBASSADOR PIPELINE · EQUITY CHECKLIST
COMPLETION & AMBASSADOR PIPELINE
12TH GRADE
Goal: Every enrolled student earns their credential before graduation. Students who need additional support are identified in September — not April. Completers become next year's ambassadors.
12
When | Activity | Purpose & Success | Audience | Point Person | Cat. | KIM
September | KIM review — completion status audit | □ Pull each student's ECC record from the KIM system — on track vs. needs additional support □ Data not entered in the system won't count toward accountability □ By Oct 1: every student who needs support has a written completion plan Success: Every student's ECC status is known by October 1. | Enrolled 12th graders | FRNYC Coordinator | Retention | A7 Support plan in place Protects D40 ECC completion
Ongoing | ECC partner coordination | □ Name a direct contact at the ECC partner institution; know all deadlines □ When a student needs support, contact the ECC liaison directly — don't wait for grades □ Explore support or withdrawal options before mid-semester, when options narrow Success: No credit lost due to a missed administrative deadline. | School / ECC partner | FRNYC Coordinator | Retention | B16 Spring ECC planning D41 ECC partner planning D42 Fall ECC roster submitted
Jan–Apr | Completion push + ambassador recruitment | □ January: verify ECC progress via KIM system; weekly check-ins for anyone behind □ Recruit 3–5 completing seniors as ambassadors — ask directly □ Ambassador role: open house, advisory visits, share their FRNYC experience Success: 90%+ earn credential before graduation; 3+ ambassadors confirmed. | Enrolled 12th graders | FRNYC Coordinator | Both | C25 Seniors: paid WBL accepted D40 ECC completion D46 Seniors: paid WBL completed
Before June 30 | End-of-year debrief | □ Coordinator + AP + Counselor: review % who completed, where students needed more support, 3 changes for next cycle □ File the debrief before June 30 — findings shape next fall's open house and feeder school priorities Success: Written debrief on file; 3 changes identified for next year. | School staff | FRNYC Coordinator | Both | D29 Next-SY implementation plan D31 Equity reflection complete
EQUITY CHECKLIST — SWD & MLL ACCESS · REVIEW AT ENROLLMENT AND MID-YEAR · LINKED TO A6 & D31
Underrepresentation is a structural challenge — not a preferences problem. Review each item at enrollment and again at mid-year. Escalate unresolved gaps to school leadership and OSP before Checkpoint C (Apr 5).
Watch For | What To Do
IEP pull-out schedules or mandated services may conflict with pathway scheduling without anyone flagging it | Cross-reference the interest survey with the master schedule before the cohort is finalized. Explore period swaps, modified pull-outs, or an alternate CCI section. Flag to AP before the cohort is locked.
Multilingual families receive outreach materials in English only | Translate all core materials (open house flyer, interest survey, orientation) into the top 3 home languages. Recruit bilingual student ambassadors. Request translation support from ENL or your network office.
ECC partner prerequisites may create barriers for SWD and MLL students who qualify via other pathways | Audit prerequisite lists annually. Identify what is a confirmed partner requirement vs. an internal assumption that can be challenged. Escalate structural barriers to your AP and OSP.
SWD / MLL enrollment in FRNYC is below their share of the school population | Set an explicit equity target before each cycle — if SWD is 20% of 9th grade, aim for 20% of the FRNYC cohort. Actively recruit early and escalate significant gaps to school leadership and OSP before October 1.
FRNYC Recruitment & Retention Playbook · FutureReady NYC / NYCPS Office of Student Pathways
5